## Document Control
Field | Details
Document Title | CampusConnect AI – Software Test Plan
Document Type | Software Testing / Quality Assurance Test Plan
Project | CampusConnect AI – Smart Campus Recruitment & Placement Management System
Version | 1.0
Document Status | Baseline
Testing Approach | Manual Testing with API and Database Validation
Frontend | React.js, JavaScript, HTML5, CSS3
Backend | Node.js, Express.js, REST APIs
Database | MongoDB with Mongoose
API Testing Tool | Postman
Database Validation | MongoDB / MongoDB Atlas
Browser Testing | Google Chrome, Microsoft Edge
Prepared By | QA / Software Testing Project

## Test Plan
Section | Details
1. Introduction | CampusConnect AI is a web-based campus recruitment and placement management system designed to connect students, recruiters and administrators. This test plan defines the testing objectives, scope, strategy, environment, deliverables, risks and completion criteria.
2. Test Objective | Verify application functionality, input validation, frontend-backend integration, REST API behavior, MongoDB persistence, authentication and authorization; identify defects; verify fixes through retesting; and perform regression, smoke, sanity, responsive and basic security testing.
3. Testing Scope | Student registration/login, profile, profile photo, resume management, campus drives, applications, application status, recruiter registration/login, recruiter dashboard, candidate management, interview management, REST APIs, MongoDB operations, UI, responsive behavior, authentication, authorization and basic security.
4. Out of Scope | Production-scale load testing, advanced penetration testing, real payment gateway testing, real email/SMS delivery validation and third-party production infrastructure testing.
5. Testing Strategy | Risk-based manual testing supported by Postman API testing and MongoDB validation. Positive and negative paths are covered, followed by integration, regression, smoke, sanity, responsive and basic security checks.
6. Test Levels | UI/system functional testing, API testing, integration testing between frontend/backend/database, database validation and regression testing.
7. Test Types | Functional, UI, validation, positive, negative, API, database, integration, smoke, sanity, regression, responsive, authentication, authorization and basic security testing.
8. Primary Modules | Student, Recruiter, Campus Drives, Applications, Candidates, Interviews and administrative/management workflows implemented in the application.
9. Student Coverage | Registration, login, profile update, profile photo, resume upload, campus drive listing, drive details, application submission, duplicate application validation, My Applications and application status.
10. Recruiter Coverage | Registration, login, dashboard, recruiter-specific drives and statistics, campus drive management, candidate management, candidate search/filtering and interview workflows.
11. API Coverage | Request/response validation, HTTP status codes, valid/invalid payloads, invalid IDs, authentication behavior, error handling and recruiter/dashboard REST endpoints.
12. Database Coverage | Student, Recruiter, Drive and Application persistence; ObjectId relationships; recruiter-drive ownership; student-drive application relationships; data integrity and credential storage.
13. Security Coverage | Authentication, protected-route access, authorization/ownership checks, invalid credential handling and password-storage validation. This is basic application-level security testing, not a penetration test.

## Modules & Coverage
Module | Key Features in Scope | Priority | Testing Types | Dependencies
Student | Registration, Login, Profile, Photo, Resume, Drives, Applications, My Applications | High | Functional, UI, Validation, Negative, Integration, Database, Regression | Backend + MongoDB
Recruiter | Registration, Login, Dashboard, Drives, Candidates, Interviews | High | Functional, UI, API, Integration, Security, Database, Regression | Backend + MongoDB
Campus Drives | Create, View, Details, Update, Active/Closed lifecycle | High | Functional, Validation, Integration, Database, Regression | Recruiter + Drive API
Applications | Apply, duplicate prevention, resume reference, status, My Applications | High | Functional, Negative, Integration, Database, Regression | Student + Drive + MongoDB
Candidates | Candidate listing, search, filtering, profile information | Medium | Functional, UI, Integration, Regression | Applications + Student
Interviews | Schedule, edit/reschedule, status, cancel | High | Functional, Integration, Validation, Regression | Application + Recruiter
REST APIs | Authentication, recruiter APIs, dashboard and related endpoints | High | API, Negative, Validation, Error Handling | Node/Express
Database | Student, Recruiter, Drive, Application models | High | Database, Integrity, Relationship, Security | MongoDB/Mongoose
Responsive UI | Major pages at mobile/tablet/desktop viewport sizes | Medium | Responsive, UI | Browser

## Environment & Tools
Category | Specification | Purpose
Frontend | React.js / JavaScript / Vite | Application UI and client-side workflows
Backend | Node.js / Express.js | REST API and server-side business logic
Database | MongoDB / Mongoose | Persistent application data
API Tool | Postman | REST API request/response validation
Database Tool | MongoDB / MongoDB Atlas | Database validation and data integrity checks
Browser | Google Chrome | Primary UI/browser testing
Browser | Microsoft Edge | Cross-browser validation
IDE | Visual Studio Code | Development and debugging
Version Control | Git / GitHub | Source and QA artifact management
Test Data | Valid, invalid, boundary and duplicate data | Positive and negative testing

## Entry Exit Criteria
Category | Criteria
Entry Criteria | Application build is available and can be started locally.
Entry Criteria | Required frontend and backend dependencies are installed.
Entry Criteria | Backend/API server is available for applicable tests.
Entry Criteria | MongoDB connection is available for database/integration tests.
Entry Criteria | Required module is sufficiently implemented for planned testing.
Entry Criteria | Test environment and test data are available.
Exit Criteria | Planned test cases are executed or explicitly marked Not Executed/Blocked.
Exit Criteria | Critical defects are identified and tracked.
Exit Criteria | Fixed defects are retested where applicable.
Exit Criteria | Regression testing is performed after relevant fixes.
Exit Criteria | Execution results and known risks are documented.
Exit Criteria | Final test summary is prepared.

## Deliverables
ID | Deliverable | Format | Purpose | Status
DEL-001 | Test Plan | XLSX / Markdown | Define testing scope, strategy and completion criteria | Prepared
DEL-002 | Test Scenarios | XLSX | High-level testing coverage | Prepared
DEL-003 | Test Cases | XLSX | Detailed executable test cases | Prepared
DEL-004 | Requirement Traceability Matrix | XLSX | Map requirements to test cases | Prepared
DEL-005 | Bug Reports | XLSX | Track defects and retesting | Prepared
DEL-006 | API Testing | XLSX | Document API test coverage | Prepared
DEL-007 | Database Testing | XLSX | Document database validation | Prepared
DEL-008 | Test Execution | XLSX | Record actual execution results | Prepared for execution
DEL-009 | Test Summary | Markdown/XLSX | Summarize testing outcome and risks | Prepared for final execution

## Risks & Mitigation
Risk ID | Risk | Impact | Likelihood | Mitigation / QA Action | Status
RISK-001 | Database/network connectivity may prevent API/database testing | High | Medium | Verify MongoDB connection and backend availability before execution | Monitor
RISK-002 | Development changes may invalidate previous results | High | High | Run regression testing after significant changes | Monitor
RISK-003 | Hardcoded/static frontend data may not represent database behavior | Medium | Medium | Add integration tests and validate API/database source of data | Open
RISK-004 | Plain-text password handling creates credential security risk | Critical | High | Use secure password hashing such as bcrypt and retest authentication/storage | Open
RISK-005 | Overly permissive update endpoint may allow unintended field updates | High | Medium | Whitelist editable fields and verify authorization/validation | Open
RISK-006 | Environment differences may affect browser/UI behavior | Medium | Medium | Perform responsive and cross-browser checks | Monitor

## Roles & Responsibilities
Role | Responsibility
Tester / QA | Analyze requirements, design scenarios/cases, execute tests, report defects, retest fixes and maintain QA artifacts.
Developer | Implement features, investigate defects, fix defects and support the test environment.
Project Owner / Team | Review requirements, prioritize defects and approve release readiness.

## Defect Management
Field | Process
Defect Identification | Record a defect when actual behavior differs from expected behavior or a security/data-integrity concern is identified.
Defect ID | Use a unique identifier such as BUG-001.
Severity | Critical, High, Medium or Low based on functional/security impact.
Priority | Critical, High, Medium or Low based on urgency for resolution.
Evidence | Include screenshots, API responses, console/network evidence or database evidence when available.
Retesting | Fixed defects are retested using the original test case.
Regression | Related and previously working functionality is tested after fixes.
Closure | Defect is closed only after the fix is verified or an explicit disposition is documented.

## Test Schedule
Phase | Activity | Output
Phase 1 | Requirement and module review | Testing scope and requirements identified
Phase 2 | Test scenario design | Test scenario workbook
Phase 3 | Test case design | Test case workbook
Phase 4 | RTM preparation | Requirement-to-test mapping
Phase 5 | Functional/UI/negative testing | Execution results + defects
Phase 6 | API testing | API execution results
Phase 7 | Database testing | Database validation results
Phase 8 | Integration testing | Integration results
Phase 9 | Regression/smoke/sanity testing | Regression and release evidence
Phase 10 | Test summary | Final QA summary and known-risk assessment