## Project title
Field | Details
Document Title | Campus Connect AI-Software Test Plan
Document Type | Software Testing Plan
Project | Campus Connect AI-Smart Campus Recruitment & Placement Management System
Prepared by | Renuka Joshi

## Test Plan
Sections | Details
1. Introduction | Campus Connect AI is a web-based recruitement and placement management system designed to connect students,recruiters and adminstrators.This test plan defines the testing objectives,scope,strategy ,enviourment,deliverables,risks and completion criteria.
2.Test Objectives | Verify applications functionality,input validation,frontend-backend integration ,REST API behaviour,MongoDB persistence,authentication and authrorization,identity defects,verify fixes through retesting and perform regression,smoke,responsive and basic security testing.
3.Testing Scope | Student registration/login,profile,profile photo,resume management,campus drives,applications,application status,recruiter registration/login,recruiter dashboard,candidate management,interview management,MongoDB operations,UI ,responsive behaviour,authentication ,authorization and basic secuirty.
4.Out of Scope | Production -scale load testing,real payment gateway testing,real email/SMS delivery validation and third-party production infrastructure testing.
5.Testing Strategy | Risk based manual testing and MongoDB validation,Positive and negative paths are covered,followed by integration ,regression,smoke,sanity,responsive and basic security checks.
6.Test Levels | UI/system functional testing,integration testing between frontend/backend/database,database validation and regression testing.
7.Test Types | Functional,UI,validation,positive,negative,database,integration,smoke,sanity,regression,responsive,authetication,authorization and basic security testing.
8.Primary Modules | Student,Recruitement,Campus drives,Applications,Candidates,Interviews and adminstrative/management workflows implemented in the application
9.Student Coverage | Registration,login,profile update,profile photo,resume upload,campusdrive listing,drive details,application submission,duplicate application validation,My application and application status
10.Recruiter Coverage | Registration,login,dashboard,recruiter-specific drives ,campus drive management,candidate management,candidate search/filtering and interview workflows
11.Database Coverage | Student,Recruiter,Drive and Application persistence,ObjecteId relationship,recruiter-drive ownership,student-drive application relationshhip,data integrity and credentials storage
12.Security Coverage | Authentication,protected-route acess,authorization/ownership checks,invalid credential handling and password-storage validation.This is basic application-level security testing not a pentration testing.

## Modules & Coverage
Module | Key features in scope | Priority | Testing Types
Student | Registration,Login,Profile,Photo,Reume,Drives,Applications,My Application | High | Functional,UI,Validation,Negative,Integration,Database,Regression
Recruiter | Registration,Login,Profile,Photo,Reume,Drives,Applications,My Application | High | Functional,UI,Validation,Security,Regression,Database
Campus Drives | Create,Update,View Details,Activate/Closed LifeCycle | High | Functional,Validation,Integration,Database,Regression
Application | Apply,view Application,View Criteria, | High | Functional,Negative,Integration,Database,Regression
Candidates | Candidate Listing,search,filtering,profile information | Medium | Functional,UI,Integration,Regression
Interviews | schedule,edit/reschedule,reject,change status | High | functional,Integration,Validation,Regression
Databse | Students,Recruiters,Drives,Application Models | High | Database,Integrity,Relationships,Security
Responsive UI | Major pages at mobile/tablet/desktop viewport sizes | medium | Responsive,UI

## Enviourment &tools
Category | Specification | Purpose
Frontend | React.js/Javascript/Vite | Application UI Client-side workflows
Backend | Node.js/Express.js | REST API and server-side business logic
Database | MongoDB | Persistent application data
Database Tool | MongoDB/MongDB Atlas | Database validation and data integrity checks
Browser | Google Chrome | Primary UI/browser testing
Browser | Microsoft Edge | Cross-browser validation
IDE | Visual Studio Code | Development anddebugging
Version Control | Github/Git | Source and QA artifact management
Test data | Valid,invalid,boundary and duplicate data | Positive and Negative testing

## Entry & Exit Criteria
Category | Criteria
Entry Criteria | Application build is available and can be started locally .
Entry Criteria | Required frontend and backend dependencies are installed.
Entry Criteria | MoongoDB connection is available for database/integration tests.
Entry Criteria | Required module is sufficiently implemented for planned testing.
Entry Criteria | test enviourment and test data are available.
Exit Criteria | Planned test cases are executed or explicitly marked Not Executed/Blocked
Exit Criteria | Critical defects are identified and tracked.
Exit Criteria | Fixed defects are retested where applicable.
Exit Criteria | Regression testing is performed after relevant fixes.
Exit criteria | Execuetion results and known risks are documented.
Exit Criteria | Final test summary is prepared.

## Deliverables
ID | Deliverable | Format | Purpose | Status
DEL-01 | Test Plan | XLSX | Define testing scope,strategy and completion criteria | Prepared
DEL-02 | Test Scenario | XLSX | High level tetsing coverage | Prepared
DEL-03 | Test Cases | XLSX | Detailed Execuetable test cases | Prepared
DEL-04 | Requirement Traceablity Matrix | XLSX | Map requirement to test cases | Prepared
DEL-05 | Bug Reports | XLSX | Track defects and retesting | Prepared
DEL-06 | Database Testing | XLSX | Document database validation | Prepared
DEL-07 | Test Execuetion | XLSX | Record actual execuetion results | Prepared for execution
DEL-08 | Test Summary | XLSX | Summarize testing outcome and risks | Prepared for final Execuetion

## Risks & Mitigation
Risk ID | Risk | Impact | Chance/Probablity | Mitigation | Status
RISK-01 | Database/network connectivity may prevent API/database testing . | High | Medium | Verify MongoDB connection and backend avaiablity before execuetion | Monitor
RISK-02 | Development changes may invalidate previous results | High | High | Run Regression testing after significant testing. | Monitor
RISK-03 | Hardcoded/static frontend data may not represent database behaviour | Medium | Medium | Add integration tests and validate database source of data | Open
RISK-04 | Plain-text password handling creates credential security risk | Critical | High | Use secure password hashing such as bcrypt and retest authentication/storage | Open
RISK-05 | Overly permissive update endpoint may allow unintended field updates | High | Medium | Whitelist editable fields and verify authorization/validation | Open
RISK-06 | Enviournment differences may affect browser/UI behavior | Medium | Medium | Perform responsive and cross-browser checks | Monitor

## Roles & Responsibilty
Roles | Responsibilty
Developer/Tester | Develop and maintain the application ,analyze requirements ,design test scenario and test cases ,execute tests,document defects,verify fixes,perform regression testing and maintain QA documentation.

## Defect Management
Field | Process
Defect Identification | Record a defect when actual behavior differs from expected behavior or a security/data-integrity concern is identified.
Defect Identification | Use a unique identifier such as BUG-01.
Severity | Critical,High,Medium or Low based on functional /security impact.
Priority | Critical,High,medium or Low based on urgency for resolution.
Evidence | Include screenshots ,console/network evidence or database evidence when available.
Retesting | Fixed defects are retested using the original test cases.
Regression | Related and previously working functionalty is tested after fixes.
Closure | Defect is closed only after the fix is verified or an explicit disposition is documented.

## Test Schedule
Phase | Activity | Output
Phase 1 | Requirement and module review | Testing scope and requirements identified
Phase 2 | Test scenario design | Test Scenario workbook
Phase 3 | Test case design | Test case workbook
Phase 4 | RTM preparation | Requirement to test mapping
Phase 5 | Functional /UI/negative testing | Execuetion results + defects
Phase 6 | Database testing | Database validation results
Phase 7 | Integration testing | Integration results
Phase 8 | Regression/smoke/sanity testing | Regression ad release evidence
Phase 9 | Test Summary | Final QA summary and known risk assesment